## Sheet1
risk_id | title | category | description | cause | trigger | affected_objective | probability | impact | risk_score | proximity | status | owner | response_strategy | response_actions | contingency_plan | residual_probability | residual_impact | residual_score | date_identified | last_updated | comments | inherent_score
R-001 | Vendor API delay | Schedule | External API delivery delay | Vendor constraints | Missed milestone | Schedule | 4 | 5 | 20 | Near-term | Open | A. Smith | Mitigate | Weekly checkpoints | Use stub interface | 2 | 4 | 8 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Vendor non-responsive | 20
R-007 | Security vulnerability | Security | Outdated dependency | Known CVE | Automated scan | Security | 4 | 5 | 20 | Near-term | Open | G. Gray | Mitigate | Patch software | Rollback to v1 | 1 | 3 | 3 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | High priority | 20
R-019 | Migration timeline | Schedule | Timeline too tight | Bad planning | Schedule slippage | Schedule | 4 | 4 | 16 | Near-term | Escalated | S. Lime | Mitigate | Add resources | Phased rollout | 2 | 2 | 4 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | High pressure | 16
R-028 | Access management | Security | Unauth access | Privilege creep | Audit fail | Security | 3 | 5 | 15 | Near-term | Escalated | B. Peach | Mitigate | Implement IAM | Manual audit | 1 | 3 | 3 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Severe risk | 15
R-004 | Scope creep | Scope | Uncontrolled features | Stakeholder demand | Change request | Scope | 4 | 3 | 12 | Near-term | Response in Progress | D. Brown | Mitigate | Strict CR process | Deny features | 2 | 2 | 4 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Monitor scope | 12
R-006 | Budget overrun | Cost | Inflation impacting hardware | Market rates | Vendor quote | Cost | 3 | 4 | 12 | Mid-term | Watching | F. Black | Transfer | Re-budget | Reduce scope | 2 | 2 | 4 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Financial pressure | 12
R-008 | Data quality issues | Data | Incomplete legacy records | Manual input | Data migration | Data | 4 | 3 | 12 | Near-term | Open | H. Blue | Mitigate | Clean data | Manual entry | 2 | 2 | 4 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Poor legacy data | 12
R-017 | Hardware shortage | Procurement | Supply chain lag | Logistics | Procurement delay | Cost | 3 | 4 | 12 | Near-term | Open | Q. Teal | Transfer | New supplier | Source alternative | 2 | 2 | 4 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Waiting on parts | 12
R-026 | Legacy code debt | Technical | Spaghetti code | Poor practices | Maintenance cost | Technical | 4 | 3 | 12 | Long-term | Watching | Z. Salmon | Mitigate | Refactor | Isolate | 2 | 2 | 4 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Slow dev | 12
R-029 | Unstable integration | Technical | Module conflict | Dependencies | System crash | Technical | 3 | 4 | 12 | Near-term | Open | C. Berry | Mitigate | Version lock | Isolate | 2 | 2 | 4 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Unstable build | 12
R-002 | Server latency | Technical | Database query optimization issues | Poor indexing | Spike in traffic | Operational | 3 | 4 | 12 | Mid-term | Watching | B. Jones | Mitigate | Optimize queries | Add read replicas | 1 | 2 | 2 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Monitoring performance | 12
R-018 | Testing environment fail | Quality | Env mismatch | Config drift | Test fail | Quality | 3 | 4 | 12 | Near-term | Response in Progress | R. Navy | Mitigate | Standardize env | Use prod env | 1 | 2 | 2 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Env unstable | 12
R-014 | Infrastructure outage | Technical | Power grid failure | Weather | Utility alert | Operational | 2 | 5 | 10 | Long-term | Open | N. Purple | Mitigate | Backup power | Cloud migration | 1 | 3 | 3 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | High impact | 10
R-003 | Compliance breach | Compliance | Data privacy regulation violation | Outdated policy | Regulatory audit | Compliance | 2 | 5 | 10 | Long-term | Open | C. White | Avoid | Update policies | Retain legal counsel | 1 | 2 | 2 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | High legal impact | 10
R-005 | Resource gap | Resource | Critical developer leave | Turnover | Hiring delays | Schedule | 3 | 3 | 9 | Near-term | Escalated | E. Green | Transfer | Hire contractor | Internal move | 2 | 2 | 4 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Urgent need | 9
R-010 | Quality defect | Quality | High bug rate | Code complexity | QA report | Quality | 3 | 3 | 9 | Near-term | Response in Progress | J. Red | Mitigate | Refactor code | Add QA hours | 2 | 2 | 4 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Reviewing code | 9
R-015 | Knowledge silo | Resource | Single person dependency | Lack of docs | Staff leave | Resource | 3 | 3 | 9 | Near-term | Open | O. Pink | Mitigate | Documentation | Knowledge transfer | 2 | 2 | 4 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | High risk | 9
R-022 | Inaccurate forecasting | Data | Model drift | Data bias | Forecast error | Data | 3 | 3 | 9 | Mid-term | Watching | V. Indigo | Mitigate | Retrain model | Use expert | 2 | 2 | 4 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Data drift | 9
R-024 | Feature bloat | Scope | Feature creep | User request | UI review | Scope | 3 | 3 | 9 | Mid-term | Open | X. Cream | Avoid | Design freeze | Cut features | 2 | 2 | 4 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Bloat risk | 9
R-021 | Team burnout | Resource | Overtime | Schedule pressure | High absenteeism | Resource | 3 | 3 | 9 | Mid-term | Open | U. Violet | Mitigate | Reduce hours | Hire support | 1 | 2 | 2 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Critical risk | 9
R-013 | External dependency | External | Regulatory delay | Gov policy | Policy shift | Compliance | 2 | 4 | 8 | Long-term | Watching | M. Bronze | Mitigate | Lobby/Influence | Pivot plan | 1 | 3 | 3 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Waiting on gov | 8
R-023 | Stakeholder turnover | Stakeholder | Key sponsor leaves | Corp reshuffle | Meeting cancellation | Stakeholder | 2 | 4 | 8 | Mid-term | Open | W. Maroon | Mitigate | Build relationship | Engage deputy | 1 | 3 | 3 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Need new sponsor | 8
R-009 | Stakeholder misalignment | Stakeholder | Conflicting project goals | Miscommunication | Steering meeting | Stakeholder | 2 | 4 | 8 | Mid-term | Watching | I. Yellow | Mitigate | Align goals | Escalate to sponsor | 1 | 2 | 2 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Group friction | 8
R-027 | Publicity risk | External | Bad press | Social feedback | User complaint | Operational | 2 | 4 | 8 | Mid-term | Open | A. Plum | Avoid | PR management | Respond fast | 1 | 2 | 2 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Monitor social | 8
R-012 | Contractor non-compliance | Procurement | Missing deliverables | Contract gaps | Audit | Procurement | 3 | 2 | 6 | Long-term | Open | L. Silver | Transfer | Legal review | Replace vendor | 1 | 2 | 2 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Contract issue | 6
R-016 | Market changes | External | Demand shift | Competition | Sales review | Operational | 2 | 3 | 6 | Mid-term | Watching | P. Orange | Accept | Watch market | Adjust strategy | 1 | 2 | 2 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Monitor | 6
R-020 | Cloud cost spike | Cost | Over-provisioning | Poor monitoring | Billing alert | Cost | 2 | 3 | 6 | Mid-term | Open | T. Olive | Mitigate | Optimize instances | Shutdown services | 1 | 2 | 2 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Monitor costs | 6
R-025 | Software licencing | Procurement | License expiry | Lack of tracking | Renewal alert | Procurement | 2 | 3 | 6 | Long-term | Open | Y. Coral | Transfer | Purchase | Compliance update | 1 | 1 | 1 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Compliance risk | 6
R-011 | Tooling failure | Operational | Pipeline downtime | Server crash | Alert trigger | Operational | 2 | 3 | 6 | Mid-term | Closed | K. Gold | Accept |  |  | 0 | 0 | 0 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Resolved | 6
R-030 | Project completion | Schedule | End of phase | Deadline | Final gate | Schedule | 1 | 1 | 1 | Long-term | Closed | D. Apricot | Accept | Final sign-off |  | 0 | 0 | 0 | 2026-06-01 00:00:00 | 2026-06-03 00:00:00 | Safe | 1